## WBS
WORK BREAKDOWN STRUCTURE (HARDWARE) |  |  | WORK BREAKDOWN STRUCTURE (SOFTWARE)
1. Insert one task for each hardware resource identified in the "Requirements". |  |  | 1. Insert one task for each software resource identified in the "Requirements".
WBS Code | WBS Description | Resources Needed | WBS Code | WBS Description | Resources Needed
H1 | Laptop |  | S1 | Understand user inputs
H1.1 | A laptop with internet access | Wi-Fi Router / Access Point | S1.1 | Detect and process user messages | JavaScript, Chatbot tool, HTML, CSS
H2 | Mouse |  | S2 | Give outputs
H2.1 | A mouse connected to a device with internet access | A laptop with internet access | S2.1 | Generate and display responses | JavaScript, output display framework, HTML, CSS
H3 | Keyboard |  | S3 | Answer questions
H3.1 | Keyboard that is connected to any device with internet access | Any device with internet access | S3.1 | Provide accurate answers to queries | NLP tool, chatbot backend, JavaScript
H4 | Mobile Phone |  | S4 | Keep conversations going
H4.1 | A Mobile Phone with voice chat feature | Speaker / Earphones | S4.1 | Maintain context and flow of dialogue | Chatbot memory module, JavaScript, session storage
Fill in your answers in the yellow boxes |  |  | Fill in your answers in the yellow boxes

## Communication Plan
COMMUNICATION PLAN
Person | Role | Communication Frequency | Format / Channel | Tasks
Fion | Researcher | Daily | WhatsApp Group Chat/Telegram Channel | H2.1, S3.1
Christabel | Tester / QA | Daily | WhatsApp Group Chat/Telegram Channel | H3.1, S4.1
Melissa | Project Manager | Daily | WhatsApp Group Chat/Telegram Channel | H1.1, S1.1
Austen | Programmer (FE& BE) | Daily | WhatsApp Group Chat/Telegram Channel | H4.1, S2.1
Fill in your answers in the yellow boxes

## Test Plan
HARDWARE TEST CASES
Case ID | Test Description | Test Designed By | Expected Results
HW1 | Device connects to Wi-Fi | Christabel | Device is connected
HW2 | Test if screen displays the full content | Melissa | Content is visible on monitor
HW3 | The user's input is displayed on the screen as they type on the keyboard | Fion | User's input displays on screen
HW4 | Test if device can smoothly scroll through content | Austen | User can scroll smoothly
SOFTWARE TEST CASES
Case ID | Test Description | Test Designed By | Expected Results
SW1 | Check if the AI detects and responds to user input | Melissa | AI responds appropriately based on the user’s input
SW2 | Verify that the output is displayed correctly on screen | Fion | Output is shown clearly with no display issues
SW3 | Test if the AI provides a correct answer to questions | Christabel | AI provides a relevant and accurate answer
SW4 | Check if the chatbot maintains conversation flow | Austen | AI maintains topic and responds smoothly
INTEGRATION TEST CASES
Case ID | Test Description | Test Designed By | Expected Results
IN1 | Verify that user input is processed and a response is shown properly | Fion | AI processes the input and displays an appropriate response
IN2 | Check if the AI maintains conversation flow using previous messages | Austen | AI continues the chat smoothly using past context
IN3 | Ensure that question input returns a clear and accurate answer | Melissa | AI provides the correct answer and displays it clearly
IN4 | Test if typing input is instantly shown and triggers AI response | Christabel | User input appears immediately and AI responds in real-time
USER ACCEPTANCE TEST CASES
Case ID | Test Description | Test Designed By | Expected Results
UA1 | User feedback is evaluated, including satisfaction and usability | Fion | Users receive accurate and easy-to-understand answers from the AI
UA2 | Prototype performs as expected in a real-world setting | Christabel | Users can type messages and get replies without errors or delays
UA3 | Prototype interaction is interactive and user-friendly | Austen | Output is readable and well-displayed across various devices
UA4 | Prototype performs under stress conditions, such as high workload or rapid data processing | Melissa | Users feel the AI understands context and continues the chat naturally
Fill in your answers in the yellow boxes

## Reference for UA
User Acceptance Test Cases
Prototype performs as expected in a controlled environment
Protoype performs as expected in a real-world setting
Prototype deployed and validated in a real-world operational setting
Prototype robustness tested in different environments (temperature, humidity, pressure, etc.)
Monitoring system tracks prototype performance in controlled environment
Monitoring system tracks prototype performance in a real-world setting
Monitoring system tracks prototype performance deployed in a real-world operational setting
Power consumption of the prototype is within XX watts / less than XXX watts
Prototype meets safety standards and regulations
Prototype performs under stress conditions, such as high workload or rapid data processing
Prototype has appropriate user access controls and encryption
Prototype interaction is interactive and user-friendly
User-feedback evaluated including usability and satisfaction